## Sheet1
ID | As a... | I want to be able to... | So that... | Priority | Assigned to | Status | Story point
| Sprint 1 |  |  | 1 |  | Not started | 33
1 | Visitor | Create an account | I can join the community | 1 |  | Done | 8
2 | Visitor | Login | I can start using the page | 1 |  | Done | 1 | Đăng kí F+B
3 | Member | Update profile | I can edit my information | 1 |  | Started | 16 | Session login
4 | Member | Rate other user | I can give a rating on the user | 3 |  | Not started | 8 | Profile F
| Sprint 2 |  |  | 1 |  | Not started | 128
5 | Visitor | View list of random user | I can get to know the page | 1 |  | Not started | 96
6 | Member | Search player by playstyle | I can duo with them | 1 |  | Not started | 16
7 | Administrator | Delete user | I can delete user from the website | 3 |  | Not started | 8
8 | Administrator | View list of users | I can mange the users | 3 |  | Not started | 8
| Sprint 3 |  |  | 2 |  | Not started | 120
9 | Administrator | Ban user | I can prevent some users from the website | 2 |  | Not started | 48
10 | Visitor | View other user's profile | I can get the user's infomation | 3 |  | Not started | 40
11 | Member | Follow other user on the platform | I can get update on my favorite player | 3 |  | Not started | 32
| Sprint 4 |  |  | 3 |  | Not started | 184
12 | Administrator | View user statistic | I can manage the website | 1 |  | Not started | 16
13 | Member | Verify the account | I can gain trust from other user | 2 |  | Not started | 64
14 | Member | Recover password | I can get my password back | 2 |  | Not started | 32
15 | Member | Chat with user | I can interact with other player | 3 |  | Not started | 8
16 | Member | Remember password | I don't have to log in manually | 3 |  | Not started | 48
17 | Administrator | Search users | I can search for specific user | 3 |  | Not started | 16